## Sheet1
| Project Name : | LESIS & HENDRIX ORTHODONTICS | Bug Report Start Date : | 20/10/2022 | Bug Report Summary
Company | Release Version : | v0.1 | Bug Report End Date : | 2022-01-11 | High | 13
| Developer Name : | N/A | Bug Report Written By : | Abdul Kuddus Nibir | Medium | 4
|  |  | Bug Report Reviewd By : | Mohoshi Hoque | Low | 5
[5 empty] | Total | 22
Bug ID | Title | Steps to Reproduce | Expected Result | Actual Result | Priority
ID-01 | Header part in chrome | Open the app in any browser | All information will be there correctly | The phone number is wrong | High
ID-02 | Nevigation bar Misaligned in Chrome | Open the app in any browser | Our practie button should maintain a distance LESIS & HENDRIX ORTHODONTICS | Our practie button is displayed on the left side of the form | Medium
ID-03 | Nevigation bar is missing in Chrome | Open the app in any browser | There should be 4 nevigation bar in the right side | there are 3 missing bar in this part | High
ID-04 | Menu Icon is missing | Open the app in any browser | There should be menu icon | they are missing | High
ID-05 | Picture have no blue border | Open the app in any browser | In This section pictures should not have blue border | Have the border on chorom | Medium
ID-06 | Follow the sequence | Open the app in any browser | our practice should be in this section | There have get to know us section | Low
ID-07 | Get to know us section | Open the app in any browser | Paragraph front should be bold | Its not bold | Low
ID-08 | Our practice section is misalign in chrome | Open the app in any browser | In figma design there have Our practice | But in chrome there have get to know us section | Low
ID-09 | Our practice section in chrome | Open the app in any browser | Paragraph front should be bold | Paragraph front should be bold | Low
ID-10 | OUR SERVICES section missalign in chrome | Open the app in any browser | Should follow the sequence | Don’t follow the sequence | High
ID-11 | OUR SERVICES section in chrome | Open the app in any browser | Paragraph should match in Braces | Don’t match the paragraph | High
ID-12 | ORTHODONTICS FOR EVERYONE section in chrome | Open the app in any browser | Picture should follow the sequence | Don’t follow the sequence | High
ID-13 | ORTHODONTICS FOR EVERYONE section in chrome | Open the app in any browser | There should have menu icon | There have no menu icon | High
ID-14 | PATIENT TESTIMONIALS section in chrome | Open the app in any browser | Should follow the sequence | Don’t follow the sequence | Medium
ID-15 | PATIENT TESTIMONIALS section in chrome | Open the app in any browser | Paragraph should match in James B. | its not match | High
ID-16 | REQUEST AN APPOINTMENT section in chrome | Open the app in any browser | Should follow the sequence | Don’t follow the sequence | Medium
ID-17 | Our location section in chrome | Open the app in any browser | It will be our locations | But in chrome it is our locations | Low
ID-18 | Our location section in chrome | Open the app in any browser | there should be correct phone number | there have wrong phone number | High
ID-19 | Our location section in chrome | Open the app in any browser | There should be a map with lockated place | there have no lockated place | High
ID-20 | Our location section in chrome | Open the app in any browser | there should have Zooming zoomout icon | there have no icon | High
ID-21 | Quick links in chrome | Open the app in any browser | there has 4 navigation | there have 2 nevigation | High
ID-22 | Contact Info in chrome | Open the app in any browser | All information will be there correctly | Phone number is wrong here | High